## JIRA_Backlog
Issue ID | Issue Type | Title | Description | Story Points | Assigned To | Branch Name | Priority | Status
JIRA-100 | Task | Create Documentation | Create SRS, JIRA Task Sheet, Presentation, Final Report | 4 | Rohit | document-setup | High | To Do
JIRA-101 | Task | Setup Flask Project | Initialize Flask app structure and virtual environment | 3 | Rohit | feature/setup-flask | High | To Do
JIRA-102 | Task | Integrate NLP Model | Load Helsinki-NLP/opus-mt-en-hi model using transformers | 8 | Aman | feature/model-integration | High | To Do
JIRA-103 | Task | Create Translation API | Build /translate POST endpoint in Flask | 5 | Sneha | feature/translation-api | High | To Do
JIRA-104 | Task | Frontend UI Design | Design HTML/CSS interface for text input and output | 5 | Priya | feature/frontend-ui | Medium | To Do
JIRA-105 | Task | Input Validation | Validate empty and invalid inputs | 2 | Rohit | feature/input-validation | Medium | To Do
JIRA-106 | Task | Error Handling | Handle server and model inference errors gracefully | 3 | Aman | feature/error-handling | Medium | To Do
JIRA-107 | Task | Testing & Debugging | Perform unit and integration testing | 5 | Sneha | feature/testing | High | To Do
JIRA-108 | Task | Dockerize Application | Create Dockerfile and test containerization | 5 | Priya | feature/docker-setup | Medium | To Do
JIRA-109 | Task | Deploy on Render | Configure deployment settings and environment variables | 8 | Rohit | feature/render-deployment | High | To Do
JIRA-110 | Task | Documentation | Prepare README and deployment guide | 3 | Sneha | feature/documentation | Low | To Do